## Sheet1
[5 empty] | Plan start | WIP | Plan Finish
[5 empty] | Actual Start | WIP | Actual Finish
|  |  | Month | Aug |  |  |  | Sept | [7 empty] | Oct | [9 empty] | Nov
|  |  | Date | 21 | 23 | 28 | 30 | 4 | 6 | 11 | 13 | 18 | 20 | 25 | 27 | 2 | 4 | 9 | 10 | 16 | 17 | 23 | 24 | 30 | 31 | 6 | 7 | 13 | 14 | 20 | 21 | 27 | 28
|  |  | Day | Tue | Thur | Tue | Thur | Tue | Thur | Tue | Thur | Tue | Thur | Tue | Thur | Tue | Thur | Tue | Wed | Tue | Wed | Tue | Wed | Tue | Wed | Tue | Wed | Tue | Wed | Tue | Wed | Tue | Wed
Stage | Task | No. of Hours
PLANNING |  | 140
Planning | Gathering Client requirement- team meetings | 25 | bar: Tue
Planning | Follow-up with clients | 30 | bar: Tue; Tue
Planning | Learning Google Analytics | 65 | bar: Tue to Tue
Planning | Timeframe | 20 | bar: Tue; Tue
INITILIZATION |  | 25
Initilization | Get Project team | 10 | bar: Tue to Wed
Initilization | Task & Time Division | 5 | bar: Tue; Wed
Initilization | Resource Collection | 10 | bar: Thur to Tue
DASHBOARD |  | 17
Dashboard | Understanding Business questions | 5 | bar: Wed to Tue
Dashboard | Desigining Dashboard visuals | 6 | bar: Tue
Dashboard | Review Dashboard with client | 2 | bar: Wed
Dashboard | Build Dashboard | 4 | bar: Tue
DEVELOPMENT |  | 84
Development | Data Collection | 20 | bar: Wed to Tue
Development | Data Cleaning | 6 | bar: Tue to Wed
Development | Data understanding | 6 | bar: Wed
Development | Machine Learning | 40 | bar: Tue to Wed
Development | Result Analysis | 12 | bar: Tue to Wed
ASSESMENT |  | 40
Assesment Deliverables | Presentation | 4 | bar: Wed to Tue
Assesment Deliverables | Critical Reflection | 4 | bar: Wed to Wed
Assesment Deliverables | Report | 32 | bar: Tue to Wed